## Sheet
Project_ID | Project_Name | Region | Business_Unit | Project_Manager | Start_Date | End_Date | Budget | Actual_Cost | Revenue | Resources_Assigned | Project_Status | Risk_Level | Client_Satisfaction | Completion_Percentage
P001 | PMO Support | US | Risk Advisory | N Singh | 2023-09-23 | 2024-06-05 | 144038 | 151231 | 163007 | 26 | Completed | Low | 3.5 | 100
P002 | Tax Transformation | Australia | Technology | P Wilson | 2025-03-28 | 2026-06-23 | 1001583 | 918154 | 907229 | 45 | On Hold | Medium | 2.6 | 1
P003 | Risk Assessment | US | Consulting | D Kumar | 2025-04-23 | 2025-09-12 | 505520 | 492101 | 514580 | 40 | Active | Medium | 1.3 | 21
P004 | Risk Assessment | Germany | Tax | K Gupta | 2023-02-20 | 2024-01-11 | 1804747 | 1968094 | 1949742 | 22 | Active | High | 4.2 | 23
P005 | PMO Support | Australia | Consulting | T Johnson | 2025-07-21 | 2026-05-22 | 251206 | 215998 | 175230 | 8 | Delayed | Medium | 4.2 | 12
P006 | Finance Transformation | US | Tax | A Sharma | 2024-09-13 | 2026-02-17 | 1804360 | 1804063 | 958388 | 3 | On Hold | High | 3.6 | 45
P007 | PMO Support | Australia | Technology | P Wilson | 2023-07-29 | 2024-02-13 | 697528 | 763967 | 808125 | 8 | On Hold | Medium | 3.2 | 23
P008 | Tax Transformation | Germany | Audit | N Singh | 2023-03-08 | 2023-10-08 | 1076655 | 1155461 | 1076669 | 42 | Delayed | Medium | 3.8 | 82
P009 | PMO Support | US | Consulting | P Wilson | 2023-08-19 | 2024-07-21 | 506278 | 434403 | 471181 | 40 | Completed | Low | 2 | 100
P010 | PMO Support | US | Risk Advisory | A Sharma | 2025-09-23 | 2026-05-15 | 947305 | 835748 | 1004969 | 44 | Active | Low | 1.7 | 48
P011 | Data Modernization | Australia | Tax | A Sharma | 2024-03-23 | 2025-02-17 | 537398 | 497907 | 535403 | 22 | Delayed | Medium | 4.8 | 32
P012 | ERP Migration | Germany | Risk Advisory | T Johnson | 2025-09-23 | 2026-07-14 | 581483 | 579404 | 801374 | 33 | Completed | High | 1.5 | 100
P013 | Tax Transformation | US | Audit | T Johnson | 2023-04-11 | 2024-08-14 | 263370 | 300781 | 300145 | 6 | Active | Medium | 3.2 | 27
P014 | AI Enablement | Australia | Audit | M Brown | 2024-07-31 | 2026-01-14 | 1428111 | 1604357 | 1632974 | 11 | Active | Medium | 4.6 | 32
P015 | Tax Transformation | US | Consulting | A Sharma | 2024-06-16 | 2025-08-29 | 405741 | 374603 | 272286 | 36 | On Hold | High | 3.2 | 43
P016 | Data Modernization | Germany | Consulting | P Wilson | 2025-07-11 | 2026-05-29 | 994614 | 985114 | 1042279 | 50 | Completed | Medium | 4.9 | 100
P017 | Tax Transformation | UK | Technology | K Gupta | 2023-09-26 | 2024-08-21 | 298267 | 308115 | 432993 | 20 | Completed | Low | 3.7 | 100
P018 | Tax Transformation | US | Consulting | M Brown | 2025-04-18 | 2026-04-20 | 1716508 | 1894619 | 1598188 | 40 | Active | Low | 4.3 | 35
P019 | Finance Transformation | Germany | Risk Advisory | M Brown | 2023-10-07 | 2025-03-28 | 596633 | 549262 | 557847 | 43 | Delayed | High | 1.6 | 15
P020 | Risk Assessment | Germany | Tax | S Lee | 2025-05-11 | 2026-06-06 | 591850 | 582542 | 819583 | 26 | Completed | Medium | 4.3 | 100
P021 | ERP Migration | UK | Audit | S Lee | 2023-10-25 | 2024-09-09 | 999127 | 1051245 | 575056 | 22 | On Hold | Medium | 3.1 | 5
P022 | Tax Transformation | US | Technology | D Kumar | 2024-06-13 | 2025-08-07 | 509249 | 550382 | 469788 | 10 | Delayed | Low | 4.2 | 29
P023 | PMO Support | India | Consulting | M Brown | 2024-06-14 | 2025-12-01 | 204680 | 196216 | 182821 | 47 | On Hold | Low | 3.1 | 2
P024 | Cyber Review | UK | Consulting | D Kumar | 2024-07-16 | 2025-11-21 | 230997 | 219377 | 160107 | 15 | Delayed | Medium | 1.8 | 10
P025 | Audit Automation | Singapore | Tax | M Brown | 2025-08-05 | 2026-09-03 | 1564858 | 1391207 | 701210 | 13 | On Hold | Medium | 4.2 | 11
P026 | Data Modernization | Germany | Technology | P Wilson | 2025-04-11 | 2025-11-14 | 1542050 | 1188525 | 973998 | 7 | Delayed | Low | 4.1 | 23
P027 | AI Enablement | UK | Audit | D Kumar | 2024-06-16 | 2025-07-31 | 651513 | 712279 | 787558 | 37 | Delayed | High | 1.4 | 20
P028 | AI Enablement | Germany | Risk Advisory | N Singh | 2024-09-28 | 2026-01-18 | 1314560 | 1190240 | 1021888 | 48 | Delayed | High | 1.8 | 31
P029 | Risk Assessment | US | Tax | P Wilson | 2024-09-17 | 2025-03-14 | 1853038 | 1771995 | 1558158 | 42 | Active | Medium | 1.3 | 82
P030 | Audit Automation | UK | Audit | D Kumar | 2024-10-06 | 2025-02-26 | 1002310 | 949614 | 1119433 | 37 | Completed | Medium | 1.9 | 100
P031 | Cyber Review | Australia | Risk Advisory | A Sharma | 2023-09-12 | 2024-07-26 | 206252 | 223034 | 240697 | 30 | Active | Low | 3.5 | 66
P032 | Audit Automation | Singapore | Technology | M Brown | 2023-02-04 | 2023-04-30 | 1030715 | 1118221 | 1231201 | 49 | Completed | Low | 3.4 | 100
P033 | ERP Migration | Germany | Audit | T Johnson | 2023-10-13 | 2025-03-11 | 377220 | 432447 | 426943 | 34 | Active | High | 2.8 | 64
P034 | AI Enablement | US | Risk Advisory | S Lee | 2024-02-16 | 2024-04-21 | 1927835 | 1735041 | 1600464 | 32 | Active | Medium | 4.8 | 70
P035 | Data Modernization | UK | Risk Advisory | A Sharma | 2024-01-14 | 2025-03-10 | 765459 | 740168 | 649519 | 29 | Active | High | 2.4 | 72
P036 | Cyber Review | Australia | Tax | R Patel | 2024-07-09 | 2025-10-15 | 1266258 | 1136265 | 1352962 | 7 | Active | Medium | 1.7 | 68
P037 | Audit Automation | India | Technology | N Singh | 2023-03-25 | 2024-03-15 | 1939451 | 1791115 | 1648240 | 49 | Delayed | Medium | 2.9 | 24
P038 | AI Enablement | Australia | Audit | S Lee | 2024-05-10 | 2024-07-17 | 406739 | 316579 | 307338 | 33 | Active | Medium | 3.2 | 36
P039 | Tax Transformation | India | Technology | A Sharma | 2024-11-26 | 2025-07-05 | 778796 | 877818 | 542292 | 28 | On Hold | Medium | 4.3 | 38
P040 | Risk Assessment | India | Risk Advisory | T Johnson | 2024-06-27 | 2025-05-12 | 604116 | 581744 | 612182 | 35 | On Hold | Low | 2.7 | 9
P041 | PMO Support | Singapore | Risk Advisory | P Wilson | 2023-04-24 | 2024-05-22 | 763242 | 841644 | 720607 | 4 | Active | Medium | 3.8 | 44
P042 | Cloud Strategy | UK | Risk Advisory | K Gupta | 2025-09-21 | 2026-02-14 | 1258277 | 1038410 | 555322 | 44 | On Hold | Low | 4.2 | 51
P043 | Risk Assessment | US | Audit | M Brown | 2025-01-22 | 2026-01-10 | 1237676 | 1141339 | 1032547 | 32 | On Hold | Low | 1.1 | 60
P044 | AI Enablement | US | Consulting | N Singh | 2023-07-10 | 2024-01-17 | 250279 | 215576 | 219327 | 50 | Delayed | Medium | 2.2 | 11
P045 | Cloud Strategy | India | Consulting | D Kumar | 2024-01-07 | 2024-07-27 | 1616764 | 1321600 | 1979293 | 21 | Completed | Medium | 1.6 | 100
P046 | Risk Assessment | Germany | Technology | R Patel | 2024-01-23 | 2024-09-04 | 1414936 | 1158115 | 1197492 | 8 | Active | Medium | 4.7 | 91
P047 | Cyber Review | US | Tax | P Wilson | 2023-10-06 | 2024-02-23 | 393293 | 363209 | 551380 | 8 | Completed | Low | 4.6 | 100
P048 | Cyber Review | India | Audit | T Johnson | 2025-01-19 | 2025-07-26 | 767698 | 879913 | 1121201 | 49 | Active | High | 4.3 | 38
P049 | AI Enablement | UK | Risk Advisory | J Smith | 2025-09-21 | 2026-09-02 | 435239 | 397935 | 301448 | 11 | Delayed | Medium | 2.8 | 24
P050 | AI Enablement | India | Technology | P Wilson | 2024-12-01 | 2025-04-27 | 990144 | 787652 | 722514 | 3 | Delayed | Medium | 1.1 | 60
P051 | ERP Migration | UK | Risk Advisory | N Singh | 2024-02-28 | 2024-05-04 | 1804627 | 1621657 | 1386104 | 36 | Active | High | 3 | 33
P052 | AI Enablement | India | Audit | N Singh | 2024-04-21 | 2025-07-15 | 1025332 | 977090 | 1293158 | 22 | Completed | Low | 4.8 | 100
P053 | Finance Transformation | UK | Risk Advisory | D Kumar | 2023-04-28 | 2024-08-30 | 1135906 | 1275534 | 1551987 | 16 | Active | Medium | 2.5 | 24
P054 | Finance Transformation | US | Consulting | T Johnson | 2024-02-20 | 2024-12-14 | 1994906 | 1741888 | 1726312 | 28 | On Hold | Low | 2.2 | 50
P055 | Cloud Strategy | UK | Consulting | S Lee | 2024-10-05 | 2025-05-14 | 1768758 | 1713953 | 1421813 | 11 | Delayed | Medium | 3 | 56
P056 | AI Enablement | India | Consulting | M Brown | 2025-04-05 | 2026-01-01 | 1109519 | 867108 | 713771 | 42 | Active | Medium | 4.2 | 24
P057 | Risk Assessment | Singapore | Tax | K Gupta | 2025-02-21 | 2025-10-22 | 434525 | 442925 | 433952 | 29 | Delayed | Low | 2.7 | 73
P058 | Cloud Strategy | India | Risk Advisory | R Patel | 2024-08-19 | 2025-06-22 | 955737 | 739853 | 656396 | 22 | Delayed | High | 4.5 | 72
P059 | AI Enablement | US | Tax | A Sharma | 2024-09-20 | 2025-08-08 | 117047 | 92215 | 140387 | 42 | Completed | Low | 3.7 | 100
P060 | Cloud Strategy | India | Risk Advisory | T Johnson | 2024-11-18 | 2025-06-05 | 848217 | 835653 | 637676 | 15 | Delayed | Low | 3.2 | 45
P061 | Finance Transformation | Germany | Tax | K Gupta | 2023-05-02 | 2024-05-27 | 1586825 | 1471934 | 1356943 | 16 | On Hold | High | 4.6 | 59
P062 | Cloud Strategy | UK | Tax | J Smith | 2023-04-26 | 2024-09-05 | 206362 | 164393 | 193974 | 9 | Delayed | Medium | 3.8 | 66
P063 | Cyber Review | Australia | Technology | J Smith | 2024-12-30 | 2025-09-10 | 822164 | 640637 | 650122 | 14 | Active | Low | 1 | 45
P064 | Data Modernization | US | Audit | S Lee | 2024-04-16 | 2024-09-14 | 1342429 | 1071406 | 1135490 | 30 | Active | High | 4.6 | 32
P065 | Cloud Strategy | Singapore | Tax | D Kumar | 2025-01-22 | 2025-10-24 | 1285035 | 1090056 | 1301116 | 18 | Delayed | Medium | 3.1 | 13
P066 | AI Enablement | India | Technology | T Johnson | 2024-04-29 | 2025-01-25 | 670654 | 737307 | 907016 | 16 | Active | High | 4.8 | 61
P067 | Data Modernization | Singapore | Technology | M Brown | 2023-06-19 | 2024-05-31 | 207037 | 194893 | 181128 | 13 | Delayed | Medium | 4.7 | 57
P068 | Tax Transformation | Australia | Technology | K Gupta | 2025-08-04 | 2026-08-30 | 1288163 | 1327400 | 1521541 | 5 | Delayed | High | 3.6 | 33
P069 | Audit Automation | US | Consulting | R Patel | 2023-03-27 | 2023-06-29 | 586510 | 588716 | 572630 | 32 | Delayed | Medium | 4.1 | 13
P070 | AI Enablement | Singapore | Consulting | S Lee | 2024-08-12 | 2025-08-31 | 596240 | 486359 | 396516 | 27 | On Hold | Medium | 2.6 | 19
P071 | Data Modernization | Australia | Tax | J Smith | 2024-04-14 | 2024-08-20 | 1730878 | 1979044 | 1588807 | 24 | Delayed | Medium | 1.2 | 76
P072 | AI Enablement | Singapore | Technology | K Gupta | 2023-12-12 | 2024-09-09 | 216498 | 211268 | 169208 | 6 | Active | Medium | 1.2 | 69
P073 | AI Enablement | Singapore | Technology | A Sharma | 2025-09-05 | 2026-05-03 | 945955 | 809014 | 659405 | 6 | Delayed | Low | 1.8 | 25
P074 | Cyber Review | UK | Consulting | T Johnson | 2025-08-26 | 2025-10-26 | 1093768 | 1004605 | 933808 | 13 | On Hold | Low | 1.6 | 59
P075 | Tax Transformation | UK | Consulting | M Brown | 2024-08-24 | 2025-02-04 | 1507604 | 1585128 | 2007003 | 38 | Completed | Low | 2.4 | 100
P076 | Risk Assessment | India | Tax | R Patel | 2023-07-06 | 2024-10-24 | 925950 | 735813 | 640691 | 25 | Delayed | Medium | 2.4 | 85
P077 | Cloud Strategy | India | Consulting | K Gupta | 2025-05-31 | 2026-06-15 | 981181 | 904784 | 1267607 | 10 | Completed | High | 4.4 | 100
P078 | Cloud Strategy | India | Risk Advisory | R Patel | 2024-07-06 | 2025-04-30 | 309068 | 259957 | 403885 | 50 | Completed | High | 1.5 | 100
P079 | Cyber Review | Singapore | Risk Advisory | T Johnson | 2025-08-08 | 2026-09-15 | 480465 | 472618 | 454643 | 14 | Active | Low | 3.3 | 47
P080 | Cloud Strategy | India | Risk Advisory | D Kumar | 2023-03-31 | 2023-07-23 | 556433 | 517777 | 540171 | 28 | On Hold | High | 4 | 55
P081 | Data Modernization | Germany | Risk Advisory | R Patel | 2023-08-18 | 2023-12-15 | 954139 | 862096 | 1247748 | 16 | Completed | High | 2.2 | 100
P082 | Risk Assessment | India | Audit | K Gupta | 2024-11-27 | 2026-05-19 | 1425425 | 1487905 | 1432247 | 7 | Delayed | Low | 1.2 | 88
P083 | Risk Assessment | Singapore | Risk Advisory | M Brown | 2023-12-26 | 2025-01-07 | 1466073 | 1405238 | 2133238 | 8 | Completed | Medium | 4.4 | 100
P084 | Data Modernization | Australia | Tax | P Wilson | 2023-10-24 | 2025-02-12 | 117319 | 101747 | 154736 | 48 | Completed | High | 1.1 | 100
P085 | Audit Automation | UK | Audit | K Gupta | 2024-03-04 | 2025-04-27 | 730355 | 729676 | 400015 | 10 | On Hold | Medium | 1.3 | 49
P086 | Cloud Strategy | US | Risk Advisory | N Singh | 2023-11-08 | 2024-10-15 | 920641 | 726858 | 497261 | 15 | On Hold | Medium | 1.9 | 40
P087 | Finance Transformation | US | Technology | N Singh | 2025-07-07 | 2026-01-03 | 1994881 | 1599841 | 1902227 | 26 | Delayed | Medium | 4.7 | 47
P088 | Cyber Review | UK | Risk Advisory | N Singh | 2024-08-08 | 2025-03-10 | 728900 | 644679 | 618071 | 48 | Active | Medium | 4.4 | 94
P089 | Finance Transformation | UK | Tax | T Johnson | 2025-08-21 | 2025-10-29 | 766671 | 585518 | 680705 | 7 | Completed | High | 1.6 | 100
P090 | Cloud Strategy | Singapore | Consulting | P Wilson | 2024-03-29 | 2025-02-12 | 936615 | 1005829 | 1184478 | 28 | Delayed | Low | 1.2 | 14
P091 | Tax Transformation | India | Consulting | R Patel | 2025-09-13 | 2026-10-21 | 619137 | 689540 | 628641 | 36 | Active | High | 3.3 | 24
P092 | Cloud Strategy | US | Technology | R Patel | 2023-02-14 | 2024-03-14 | 1594235 | 1586162 | 1465618 | 6 | On Hold | Low | 3.6 | 59
P093 | Cloud Strategy | Australia | Risk Advisory | D Kumar | 2024-03-23 | 2024-07-24 | 148541 | 168628 | 193651 | 4 | Delayed | High | 4.1 | 48
P094 | Cloud Strategy | UK | Risk Advisory | R Patel | 2024-04-11 | 2024-09-27 | 873514 | 1000736 | 1000423 | 22 | On Hold | High | 2.5 | 6
P095 | ERP Migration | US | Audit | T Johnson | 2024-03-11 | 2025-03-08 | 1456571 | 1373536 | 1996181 | 27 | Completed | Low | 3.3 | 100
P096 | PMO Support | Germany | Tax | A Sharma | 2023-05-09 | 2024-10-04 | 1185003 | 1180204 | 1490483 | 35 | Active | High | 1.1 | 72
P097 | Cyber Review | Australia | Audit | K Gupta | 2025-02-17 | 2026-06-25 | 1248164 | 1130179 | 1381680 | 50 | Active | High | 3.7 | 32
P098 | Data Modernization | India | Audit | J Smith | 2025-08-22 | 2027-02-09 | 1236777 | 1274731 | 1044744 | 49 | Active | High | 3.9 | 44
P099 | Risk Assessment | India | Consulting | M Brown | 2024-06-15 | 2025-05-21 | 1510767 | 1229445 | 1954758 | 17 | Completed | Low | 3.5 | 100
P100 | ERP Migration | Singapore | Audit | P Wilson | 2024-08-25 | 2024-11-24 | 780357 | 709097 | 893734 | 15 | Active | Low | 3.4 | 59
P101 | Cloud Strategy | India | Audit | S Lee | 2025-05-28 | 2026-09-07 | 1111081 | 835698 | 933251 | 24 | Completed | Medium | 2.7 | 100
P102 | PMO Support | India | Audit | M Brown | 2024-09-06 | 2025-08-07 | 1297829 | 1345109 | 2041353 | 24 | Completed | High | 4.7 | 100
P103 | Finance Transformation | India | Consulting | K Gupta | 2025-02-11 | 2026-01-31 | 583261 | 648965 | 450334 | 6 | On Hold | Low | 1.2 | 26
P104 | Audit Automation | Germany | Technology | A Sharma | 2023-10-06 | 2024-02-15 | 1555224 | 1773184 | 1529212 | 32 | Delayed | Low | 1 | 24
P105 | AI Enablement | US | Consulting | K Gupta | 2023-09-19 | 2024-02-26 | 1722065 | 1624908 | 1872426 | 40 | Delayed | Medium | 1.6 | 69
P106 | PMO Support | US | Consulting | T Johnson | 2023-04-04 | 2023-09-22 | 1506980 | 1244972 | 1606342 | 45 | Active | Low | 5 | 74
P107 | Risk Assessment | US | Consulting | P Wilson | 2023-07-29 | 2024-02-18 | 1700700 | 1580673 | 1962503 | 40 | Active | Medium | 2.6 | 70
P108 | ERP Migration | UK | Technology | M Brown | 2024-05-06 | 2024-11-28 | 1897897 | 2013603 | 1889975 | 30 | Delayed | Low | 2.3 | 12
P109 | AI Enablement | Germany | Audit | J Smith | 2023-09-27 | 2024-03-12 | 872398 | 876084 | 877492 | 28 | Active | Medium | 4.8 | 74
P110 | AI Enablement | India | Consulting | K Gupta | 2025-04-13 | 2026-07-12 | 1587906 | 1666819 | 1896420 | 37 | Active | High | 2.9 | 30
P111 | Finance Transformation | Singapore | Consulting | A Sharma | 2023-03-09 | 2023-09-24 | 211280 | 182478 | 135672 | 38 | Delayed | Medium | 4 | 40
P112 | Audit Automation | UK | Consulting | J Smith | 2023-08-29 | 2024-02-29 | 1233315 | 1210834 | 1191049 | 10 | On Hold | High | 2.2 | 39
P113 | Cloud Strategy | Germany | Technology | D Kumar | 2023-09-09 | 2024-09-03 | 1450725 | 1663622 | 2043167 | 24 | Completed | High | 4 | 100
P114 | Audit Automation | Germany | Tax | D Kumar | 2023-09-22 | 2025-02-27 | 726594 | 574393 | 724763 | 9 | Active | High | 1.6 | 58
P115 | ERP Migration | India | Technology | P Wilson | 2023-09-15 | 2023-12-25 | 994685 | 1074264 | 1103755 | 18 | On Hold | High | 4.7 | 56
P116 | ERP Migration | UK | Consulting | N Singh | 2025-02-28 | 2025-11-23 | 1670232 | 1294767 | 959155 | 50 | Delayed | Medium | 4.8 | 43
P117 | Audit Automation | India | Audit | D Kumar | 2025-04-07 | 2026-07-12 | 897427 | 814914 | 811334 | 42 | Delayed | Medium | 1.4 | 83
P118 | Tax Transformation | Singapore | Tax | A Sharma | 2024-12-25 | 2025-08-04 | 925244 | 1055342 | 935654 | 20 | On Hold | Low | 1.7 | 58
P119 | Cyber Review | US | Risk Advisory | M Brown | 2024-09-26 | 2025-01-25 | 1112562 | 1033358 | 984091 | 32 | On Hold | Medium | 1.2 | 4
P120 | Finance Transformation | Australia | Tax | T Johnson | 2024-08-08 | 2025-12-18 | 479047 | 526749 | 567378 | 22 | Active | High | 2.3 | 91
P121 | Risk Assessment | US | Audit | K Gupta | 2023-10-12 | 2024-01-14 | 1609870 | 1522259 | 1745083 | 31 | Completed | Medium | 1.2 | 100
P122 | Cyber Review | Australia | Audit | S Lee | 2024-05-21 | 2025-04-06 | 1499170 | 1338736 | 1402711 | 41 | On Hold | Medium | 2.5 | 47
P123 | AI Enablement | UK | Consulting | N Singh | 2023-07-12 | 2023-09-24 | 1616839 | 1829569 | 1781452 | 39 | Delayed | Low | 2.7 | 88
P124 | Cyber Review | UK | Technology | S Lee | 2024-09-13 | 2025-11-27 | 1684086 | 1493628 | 1799210 | 47 | Completed | Low | 2.4 | 100
P125 | AI Enablement | US | Consulting | N Singh | 2024-07-26 | 2025-02-14 | 1714267 | 1666658 | 1721422 | 46 | Active | Low | 3.3 | 70
P126 | Finance Transformation | India | Technology | N Singh | 2023-08-11 | 2024-01-26 | 630207 | 514453 | 625331 | 39 | Active | Medium | 4.7 | 51
P127 | ERP Migration | India | Technology | T Johnson | 2024-05-13 | 2025-06-25 | 283934 | 292750 | 239486 | 22 | Active | Medium | 3.1 | 89
P128 | Cyber Review | US | Risk Advisory | J Smith | 2023-01-02 | 2023-08-15 | 1454160 | 1642390 | 2032978 | 13 | Active | Medium | 4.5 | 93
P129 | Tax Transformation | Singapore | Risk Advisory | J Smith | 2023-06-07 | 2024-07-03 | 1398944 | 1058821 | 1076149 | 43 | On Hold | Medium | 1.8 | 16
P130 | Cyber Review | Germany | Audit | J Smith | 2023-04-12 | 2023-07-19 | 1197268 | 1306790 | 1860153 | 5 | Completed | High | 1 | 100
P131 | Audit Automation | US | Tax | R Patel | 2024-06-13 | 2025-08-01 | 265691 | 251812 | 298761 | 22 | Active | High | 2.1 | 37
P132 | Risk Assessment | India | Risk Advisory | D Kumar | 2024-11-30 | 2026-03-22 | 1590864 | 1509588 | 2032003 | 30 | Completed | High | 3.2 | 100
P133 | Cloud Strategy | India | Audit | D Kumar | 2024-04-03 | 2025-03-19 | 870125 | 819056 | 712502 | 3 | Delayed | High | 3 | 75
P134 | Risk Assessment | India | Consulting | M Brown | 2025-04-23 | 2025-08-22 | 1758877 | 1692664 | 1838781 | 45 | Active | High | 3.4 | 64
P135 | Cloud Strategy | US | Tax | P Wilson | 2025-05-30 | 2025-10-10 | 1312543 | 1267491 | 872849 | 30 | On Hold | Low | 1.2 | 6
P136 | ERP Migration | Germany | Technology | N Singh | 2024-11-11 | 2025-11-14 | 1384213 | 1560387 | 1570721 | 42 | Delayed | Low | 1.7 | 80
P137 | Cloud Strategy | India | Tax | R Patel | 2023-05-04 | 2024-04-04 | 780443 | 830234 | 955850 | 20 | Active | High | 4.1 | 33
P138 | Risk Assessment | US | Technology | R Patel | 2024-05-08 | 2025-03-26 | 874692 | 874067 | 992678 | 19 | Active | High | 2 | 36
P139 | PMO Support | Singapore | Risk Advisory | N Singh | 2023-04-22 | 2023-12-12 | 1894051 | 1954841 | 2623843 | 31 | Completed | Medium | 4.3 | 100
P140 | ERP Migration | US | Tax | S Lee | 2025-05-12 | 2026-10-22 | 1492486 | 1252356 | 711159 | 11 | On Hold | Low | 4.4 | 19
P141 | Cyber Review | Singapore | Tax | J Smith | 2023-07-14 | 2024-01-31 | 600470 | 503090 | 619902 | 39 | Completed | Low | 3.4 | 100
P142 | Finance Transformation | Singapore | Risk Advisory | T Johnson | 2024-10-29 | 2025-12-08 | 290456 | 245844 | 224804 | 48 | On Hold | Medium | 2.5 | 59
P143 | Risk Assessment | Germany | Technology | N Singh | 2024-12-21 | 2025-05-26 | 1156574 | 1060639 | 894238 | 39 | On Hold | High | 3.9 | 50
P144 | ERP Migration | Germany | Audit | T Johnson | 2023-02-02 | 2024-03-02 | 582666 | 591657 | 624325 | 32 | Completed | Low | 2.5 | 100
P145 | Tax Transformation | Singapore | Risk Advisory | P Wilson | 2024-12-13 | 2025-08-12 | 1201121 | 942069 | 833008 | 3 | On Hold | Low | 2.3 | 49
P146 | Finance Transformation | Germany | Technology | D Kumar | 2023-03-02 | 2024-07-01 | 596178 | 596083 | 699789 | 41 | Completed | Medium | 3.1 | 100
P147 | Risk Assessment | India | Technology | P Wilson | 2025-05-04 | 2025-10-19 | 253745 | 219697 | 157109 | 17 | Delayed | Low | 4.3 | 74
P148 | Cyber Review | US | Tax | D Kumar | 2023-12-02 | 2025-04-13 | 1920246 | 1673506 | 1258662 | 15 | Delayed | Low | 2.9 | 59
P149 | Cloud Strategy | Singapore | Technology | R Patel | 2025-07-06 | 2026-10-06 | 1658225 | 1618831 | 1291950 | 44 | Delayed | Medium | 3.8 | 33
P150 | ERP Migration | Australia | Tax | N Singh | 2023-07-25 | 2024-10-30 | 361099 | 400568 | 389005 | 9 | Delayed | Low | 2.1 | 81
P151 | Finance Transformation | Germany | Risk Advisory | J Smith | 2025-05-11 | 2026-08-10 | 290592 | 244974 | 239240 | 28 | Delayed | Low | 2 | 58
P152 | Audit Automation | UK | Technology | P Wilson | 2024-02-06 | 2024-09-11 | 1428837 | 1392919 | 1763574 | 36 | Completed | Low | 4.5 | 100
P153 | Audit Automation | Germany | Audit | R Patel | 2025-07-26 | 2025-09-30 | 1246218 | 1216063 | 1388244 | 50 | Delayed | Low | 4.2 | 85
P154 | ERP Migration | Australia | Tax | M Brown | 2024-06-11 | 2025-05-16 | 1475747 | 1454538 | 1644601 | 44 | Active | Low | 3.1 | 81
P155 | Cloud Strategy | Germany | Audit | N Singh | 2024-08-19 | 2025-08-23 | 339514 | 358351 | 425401 | 22 | Delayed | Medium | 1.8 | 20
P156 | Tax Transformation | US | Consulting | N Singh | 2024-08-20 | 2025-07-31 | 269405 | 280512 | 301500 | 40 | On Hold | Medium | 3.1 | 23
P157 | Cyber Review | Singapore | Technology | J Smith | 2025-01-13 | 2025-06-19 | 107079 | 116440 | 126951 | 23 | Completed | Low | 2.7 | 100
P158 | Audit Automation | Singapore | Audit | N Singh | 2023-09-22 | 2024-03-31 | 794560 | 647199 | 741982 | 44 | Active | High | 4.6 | 49
P159 | Tax Transformation | UK | Audit | D Kumar | 2023-09-27 | 2023-12-31 | 870016 | 862569 | 1007340 | 49 | Active | High | 2.7 | 87
P160 | Audit Automation | Singapore | Tax | J Smith | 2024-05-19 | 2025-03-17 | 1479417 | 1553102 | 1980265 | 30 | Active | High | 4.6 | 44
P161 | ERP Migration | UK | Technology | J Smith | 2023-05-05 | 2024-02-19 | 338788 | 338473 | 386559 | 42 | Delayed | High | 1.4 | 46
P162 | Data Modernization | India | Technology | R Patel | 2025-07-31 | 2026-04-01 | 1326101 | 1364271 | 1686568 | 47 | Completed | Medium | 3 | 100
P163 | PMO Support | US | Consulting | D Kumar | 2025-04-11 | 2025-10-25 | 1979291 | 2043603 | 2221736 | 31 | On Hold | Medium | 1.1 | 20
P164 | Risk Assessment | Singapore | Risk Advisory | A Sharma | 2023-11-11 | 2024-01-25 | 1437183 | 1558600 | 1808720 | 38 | Active | Low | 4.6 | 42
P165 | Audit Automation | Australia | Risk Advisory | A Sharma | 2023-03-15 | 2023-06-07 | 118306 | 114878 | 74485 | 21 | On Hold | Medium | 2.4 | 12
P166 | PMO Support | UK | Tax | K Gupta | 2025-07-05 | 2026-12-03 | 1963210 | 2225758 | 2619456 | 34 | Active | Low | 4.8 | 65
P167 | Data Modernization | US | Audit | D Kumar | 2023-10-10 | 2024-03-27 | 913991 | 748497 | 692915 | 21 | On Hold | High | 2.5 | 1
P168 | Finance Transformation | Australia | Risk Advisory | K Gupta | 2023-07-12 | 2024-09-14 | 297755 | 236011 | 219798 | 11 | Delayed | Medium | 4 | 89
P169 | Audit Automation | India | Audit | N Singh | 2023-09-07 | 2024-03-03 | 1612795 | 1255913 | 1100424 | 17 | On Hold | Low | 3.9 | 38
P170 | Tax Transformation | Germany | Tax | K Gupta | 2024-12-24 | 2025-08-09 | 384745 | 350901 | 298061 | 16 | On Hold | Low | 4.4 | 4
P171 | Risk Assessment | Singapore | Technology | J Smith | 2025-07-17 | 2026-04-15 | 1981757 | 1668919 | 1881058 | 8 | Delayed | Medium | 2.5 | 44
P172 | PMO Support | Australia | Risk Advisory | A Sharma | 2024-12-26 | 2026-02-19 | 665342 | 758557 | 645587 | 12 | Delayed | High | 2.1 | 65
P173 | PMO Support | Singapore | Tax | J Smith | 2023-07-22 | 2024-05-04 | 1065768 | 1213153 | 1268598 | 25 | Active | High | 2.5 | 41
P174 | AI Enablement | US | Risk Advisory | P Wilson | 2023-11-29 | 2025-02-05 | 1998585 | 2263677 | 2867609 | 18 | Completed | Low | 3.4 | 100
P175 | Tax Transformation | UK | Audit | K Gupta | 2025-09-03 | 2026-09-21 | 939856 | 1067681 | 1290661 | 17 | Completed | High | 2.7 | 100
P176 | ERP Migration | India | Tax | M Brown | 2025-04-14 | 2026-07-13 | 1221517 | 1369171 | 1085303 | 23 | On Hold | Low | 4 | 22
P177 | Risk Assessment | Singapore | Risk Advisory | P Wilson | 2023-12-06 | 2024-09-26 | 1320894 | 1042793 | 1269709 | 48 | Completed | Medium | 4.8 | 100
P178 | Finance Transformation | Singapore | Risk Advisory | D Kumar | 2024-12-24 | 2025-08-27 | 1580820 | 1469939 | 1410774 | 28 | On Hold | High | 3.9 | 26
P179 | Risk Assessment | US | Risk Advisory | J Smith | 2025-04-15 | 2026-10-03 | 1661594 | 1726050 | 2562441 | 36 | Completed | High | 1.4 | 100
P180 | Finance Transformation | Germany | Consulting | P Wilson | 2024-05-09 | 2025-02-15 | 323991 | 270702 | 233466 | 15 | On Hold | Low | 1.2 | 2
P181 | Tax Transformation | Singapore | Technology | A Sharma | 2024-04-06 | 2024-08-02 | 1031539 | 917584 | 883642 | 46 | Delayed | Medium | 3.6 | 75
P182 | Cyber Review | Singapore | Audit | A Sharma | 2025-08-07 | 2026-04-10 | 954561 | 1034729 | 1212597 | 21 | Delayed | High | 3 | 54
P183 | Audit Automation | Singapore | Risk Advisory | A Sharma | 2024-06-07 | 2025-08-09 | 1312744 | 1007911 | 1075911 | 6 | Delayed | Medium | 4.6 | 56
P184 | Audit Automation | Singapore | Technology | P Wilson | 2024-02-24 | 2024-05-13 | 437902 | 442445 | 333260 | 3 | On Hold | Medium | 1.2 | 48
P185 | Finance Transformation | Germany | Risk Advisory | P Wilson | 2023-07-26 | 2024-04-11 | 1545095 | 1407366 | 1619790 | 17 | Delayed | Low | 3.5 | 40
P186 | Data Modernization | US | Consulting | M Brown | 2024-04-14 | 2024-11-23 | 452333 | 422710 | 445041 | 44 | Completed | Medium | 3.7 | 100
P187 | Audit Automation | Germany | Consulting | D Kumar | 2024-07-31 | 2025-05-18 | 592320 | 633628 | 326811 | 20 | On Hold | High | 2.3 | 50
P188 | ERP Migration | Australia | Audit | M Brown | 2023-01-28 | 2023-05-10 | 1207352 | 1275182 | 1572361 | 24 | Active | High | 3.4 | 88
P189 | Tax Transformation | Germany | Tax | K Gupta | 2025-04-02 | 2026-01-18 | 1732019 | 1765490 | 1862341 | 15 | Completed | Medium | 4.9 | 100
P190 | AI Enablement | Australia | Audit | R Patel | 2025-07-22 | 2025-12-17 | 1839520 | 1641104 | 2358882 | 13 | Completed | Low | 4.4 | 100
P191 | ERP Migration | India | Audit | D Kumar | 2023-04-18 | 2024-03-25 | 349843 | 331599 | 254619 | 50 | Delayed | Low | 4.8 | 48
P192 | Cyber Review | US | Audit | P Wilson | 2024-11-06 | 2025-09-04 | 901804 | 1002182 | 754499 | 8 | On Hold | Low | 3.1 | 32
P193 | Cyber Review | US | Consulting | J Smith | 2024-06-13 | 2025-01-28 | 1773645 | 1714370 | 1619911 | 14 | Delayed | Low | 2.5 | 15
P194 | ERP Migration | Germany | Consulting | N Singh | 2025-08-07 | 2026-06-03 | 674084 | 668938 | 799904 | 41 | Delayed | Low | 3.4 | 75
P195 | Cyber Review | Germany | Audit | J Smith | 2025-08-13 | 2026-05-04 | 1260762 | 1289384 | 735458 | 40 | On Hold | High | 2 | 10
P196 | PMO Support | US | Consulting | M Brown | 2024-03-10 | 2025-01-03 | 1783062 | 1969937 | 1729379 | 32 | Delayed | Medium | 4.1 | 60
P197 | Tax Transformation | Australia | Audit | R Patel | 2025-05-22 | 2026-09-09 | 310740 | 355236 | 284286 | 5 | Delayed | Low | 4.3 | 32
P198 | Risk Assessment | Germany | Technology | A Sharma | 2023-02-26 | 2023-11-22 | 1521034 | 1169402 | 925944 | 38 | Delayed | High | 1.2 | 38
P199 | Audit Automation | Singapore | Technology | A Sharma | 2025-01-13 | 2026-06-18 | 1095007 | 991859 | 1158520 | 46 | Active | High | 1.8 | 94
P200 | Data Modernization | Singapore | Risk Advisory | T Johnson | 2024-02-19 | 2025-01-23 | 1600455 | 1805674 | 1258503 | 11 | On Hold | High | 1.6 | 26
P201 | Audit Automation | US | Technology | S Lee | 2025-04-02 | 2025-12-03 | 1728241 | 1581410 | 1136708 | 27 | On Hold | Low | 2.4 | 41
P202 | PMO Support | India | Tax | A Sharma | 2024-12-15 | 2025-11-29 | 1328948 | 1392406 | 885545 | 23 | On Hold | Medium | 1.7 | 24
P203 | Cyber Review | Germany | Risk Advisory | S Lee | 2025-06-29 | 2026-03-19 | 1895470 | 1561455 | 1276553 | 39 | Delayed | Medium | 4.4 | 59
P204 | Data Modernization | Australia | Technology | A Sharma | 2023-08-26 | 2025-02-14 | 1345143 | 1033465 | 769414 | 49 | On Hold | High | 3.2 | 19
P205 | Audit Automation | India | Risk Advisory | T Johnson | 2024-06-24 | 2025-05-26 | 1438775 | 1447267 | 1708495 | 6 | Completed | Low | 4.6 | 100
P206 | Cloud Strategy | US | Risk Advisory | M Brown | 2025-06-09 | 2026-07-07 | 673315 | 613664 | 533312 | 3 | On Hold | High | 2.6 | 12
P207 | AI Enablement | Australia | Tax | S Lee | 2025-05-15 | 2025-09-27 | 1177967 | 1333019 | 1003676 | 43 | Delayed | High | 2.1 | 34
P208 | Tax Transformation | US | Technology | J Smith | 2023-06-14 | 2024-02-08 | 332364 | 267434 | 254313 | 4 | Delayed | Medium | 3.9 | 67
P209 | Audit Automation | India | Audit | S Lee | 2025-07-16 | 2026-07-29 | 273988 | 313725 | 418206 | 13 | Completed | Medium | 2.4 | 100
P210 | AI Enablement | Singapore | Technology | K Gupta | 2025-03-04 | 2025-09-28 | 1154714 | 925466 | 1382301 | 38 | Completed | Low | 2 | 100
P211 | Cloud Strategy | Australia | Technology | J Smith | 2023-05-13 | 2024-07-04 | 926154 | 1059337 | 1237980 | 50 | Completed | Medium | 5 | 100
P212 | Tax Transformation | Germany | Audit | R Patel | 2025-03-03 | 2026-05-21 | 1707665 | 1881792 | 2278509 | 39 | Active | Low | 2.8 | 40
P213 | Tax Transformation | Singapore | Audit | N Singh | 2023-12-25 | 2024-09-09 | 1351869 | 1417338 | 1573968 | 6 | Active | High | 4 | 40
P214 | Risk Assessment | Germany | Technology | N Singh | 2024-01-11 | 2024-11-11 | 1560216 | 1602308 | 2539337 | 34 | Completed | High | 1.8 | 100
P215 | Finance Transformation | UK | Consulting | T Johnson | 2025-07-22 | 2026-01-18 | 763611 | 632605 | 631151 | 26 | Delayed | High | 1.4 | 52
P216 | AI Enablement | Australia | Consulting | K Gupta | 2024-01-15 | 2024-10-31 | 1624140 | 1748589 | 2144359 | 11 | Completed | Medium | 4 | 100
P217 | Cyber Review | India | Tax | M Brown | 2023-12-16 | 2025-02-16 | 449848 | 456876 | 514223 | 42 | Completed | High | 4.9 | 100
P218 | AI Enablement | India | Tax | A Sharma | 2023-08-12 | 2024-05-28 | 261259 | 274867 | 397335 | 15 | Completed | Low | 4.1 | 100
P219 | Risk Assessment | Germany | Risk Advisory | T Johnson | 2025-02-26 | 2026-06-10 | 1037568 | 851199 | 622281 | 28 | Delayed | High | 1.8 | 21
P220 | Cloud Strategy | US | Consulting | K Gupta | 2024-11-10 | 2025-02-24 | 1367727 | 1057209 | 1227842 | 7 | Active | Low | 1.8 | 82
P221 | PMO Support | US | Risk Advisory | P Wilson | 2023-05-18 | 2024-04-24 | 914542 | 805417 | 661620 | 30 | Delayed | Low | 4.7 | 59
P222 | Risk Assessment | UK | Risk Advisory | D Kumar | 2025-05-02 | 2026-07-27 | 1525261 | 1653724 | 1530563 | 20 | On Hold | Medium | 3.6 | 36
P223 | PMO Support | India | Consulting | P Wilson | 2024-06-05 | 2025-06-21 | 833111 | 918065 | 1050220 | 18 | Delayed | High | 2.4 | 31
P224 | PMO Support | US | Risk Advisory | P Wilson | 2023-12-09 | 2024-07-20 | 418107 | 346046 | 302703 | 15 | Delayed | High | 4.5 | 82
P225 | PMO Support | UK | Risk Advisory | P Wilson | 2023-05-17 | 2024-01-04 | 1645405 | 1553779 | 2053017 | 32 | Completed | Medium | 4.7 | 100
P226 | Cyber Review | UK | Risk Advisory | J Smith | 2023-03-01 | 2023-09-14 | 1598274 | 1531522 | 1379732 | 48 | On Hold | Medium | 4.5 | 2
P227 | ERP Migration | US | Risk Advisory | N Singh | 2023-02-09 | 2023-05-23 | 929665 | 728488 | 585380 | 20 | Active | High | 4.2 | 46
P228 | Finance Transformation | Australia | Risk Advisory | D Kumar | 2023-12-20 | 2024-05-05 | 1421507 | 1184283 | 1130457 | 37 | Delayed | Low | 4.9 | 66
P229 | Tax Transformation | Germany | Tax | J Smith | 2023-04-28 | 2024-02-09 | 1042556 | 1160074 | 1504470 | 47 | Active | High | 2.5 | 26
P230 | AI Enablement | Australia | Risk Advisory | M Brown | 2024-02-26 | 2024-09-28 | 706216 | 794509 | 1057552 | 46 | Completed | High | 1.8 | 100
P231 | AI Enablement | India | Tax | P Wilson | 2023-02-06 | 2023-06-20 | 619166 | 509280 | 493726 | 12 | Active | High | 3.8 | 78
P232 | Cloud Strategy | Germany | Risk Advisory | R Patel | 2024-02-10 | 2024-10-06 | 1502063 | 1224857 | 1836749 | 26 | Completed | Medium | 2.6 | 100
P233 | Audit Automation | India | Consulting | N Singh | 2024-12-08 | 2025-10-28 | 351514 | 298787 | 377236 | 46 | Active | Low | 1.7 | 66
P234 | Finance Transformation | UK | Tax | J Smith | 2023-09-10 | 2024-04-05 | 170907 | 129760 | 165634 | 46 | Active | High | 1.2 | 85
P235 | AI Enablement | Germany | Technology | M Brown | 2023-04-17 | 2024-07-16 | 815329 | 803639 | 860052 | 27 | Delayed | High | 3.1 | 82
P236 | Tax Transformation | US | Consulting | P Wilson | 2024-02-04 | 2024-10-30 | 533888 | 561936 | 652751 | 26 | Active | Medium | 2.6 | 84
P237 | PMO Support | US | Audit | D Kumar | 2025-09-16 | 2025-11-21 | 897831 | 977534 | 1032846 | 37 | Delayed | High | 4.3 | 78
P238 | Audit Automation | Singapore | Tax | R Patel | 2024-09-24 | 2025-01-09 | 548973 | 447141 | 273939 | 43 | On Hold | Medium | 1.4 | 4
P239 | AI Enablement | UK | Tax | D Kumar | 2024-10-27 | 2025-10-02 | 1487607 | 1700438 | 2657276 | 29 | Completed | Low | 1.7 | 100
P240 | Audit Automation | Germany | Tax | K Gupta | 2025-03-24 | 2026-06-30 | 503658 | 494617 | 448506 | 35 | On Hold | High | 3.9 | 22
P241 | Risk Assessment | Australia | Tax | J Smith | 2024-01-07 | 2024-04-05 | 704312 | 745739 | 784830 | 32 | Active | Medium | 2.4 | 33
P242 | Tax Transformation | India | Technology | K Gupta | 2024-02-28 | 2024-06-30 | 682943 | 785021 | 802625 | 36 | Active | Low | 3.8 | 37
P243 | ERP Migration | US | Risk Advisory | M Brown | 2025-01-15 | 2026-05-02 | 1226025 | 1155361 | 1497414 | 46 | Completed | Medium | 2.2 | 100
P244 | Cyber Review | India | Consulting | R Patel | 2023-09-23 | 2024-12-31 | 1173804 | 1176681 | 995586 | 9 | Active | Low | 2.8 | 83
P245 | Tax Transformation | India | Technology | T Johnson | 2024-09-05 | 2025-12-17 | 1950972 | 1659325 | 1447868 | 41 | Active | Low | 1.6 | 56
P246 | Cloud Strategy | Australia | Audit | M Brown | 2024-08-29 | 2025-09-06 | 1322775 | 1284603 | 1363063 | 13 | On Hold | Low | 3.8 | 4
P247 | Risk Assessment | US | Tax | N Singh | 2024-12-29 | 2025-08-18 | 439779 | 342880 | 448581 | 26 | Completed | Low | 5 | 100
P248 | Risk Assessment | US | Technology | R Patel | 2023-04-26 | 2023-09-11 | 1091716 | 941116 | 504508 | 10 | On Hold | Low | 2.6 | 33
P249 | Data Modernization | Germany | Audit | S Lee | 2023-10-16 | 2024-11-17 | 403621 | 389255 | 552644 | 7 | Completed | High | 1.1 | 100
P250 | Risk Assessment | Australia | Audit | J Smith | 2024-07-04 | 2025-12-17 | 1135230 | 1224991 | 1438518 | 6 | Completed | High | 3.5 | 100
P251 | AI Enablement | Germany | Technology | P Wilson | 2023-06-20 | 2024-08-04 | 1295199 | 1312326 | 1058090 | 11 | On Hold | Low | 1 | 14
P252 | Finance Transformation | India | Audit | R Patel | 2025-09-25 | 2026-10-26 | 1860986 | 1616955 | 2453216 | 16 | Completed | Low | 3.2 | 100
P253 | Data Modernization | UK | Risk Advisory | T Johnson | 2024-09-29 | 2025-11-28 | 1694074 | 1576712 | 1412857 | 36 | Active | Medium | 3.6 | 60
P254 | Finance Transformation | Germany | Risk Advisory | S Lee | 2024-01-21 | 2025-03-01 | 1699077 | 1765854 | 1781657 | 25 | Delayed | High | 3.2 | 70
P255 | Cyber Review | UK | Technology | D Kumar | 2024-08-19 | 2025-02-19 | 1775553 | 1458602 | 1915460 | 48 | Completed | High | 3 | 100
P256 | Finance Transformation | India | Tax | S Lee | 2024-07-08 | 2025-09-16 | 1304276 | 1115812 | 1536835 | 16 | Completed | High | 2.6 | 100
P257 | Risk Assessment | Singapore | Tax | M Brown | 2023-06-19 | 2024-05-27 | 1781017 | 2004277 | 2641261 | 15 | Completed | High | 3.9 | 100
P258 | ERP Migration | US | Audit | T Johnson | 2024-07-12 | 2025-08-19 | 1181260 | 936315 | 628539 | 4 | On Hold | High | 3.6 | 7
P259 | Tax Transformation | India | Technology | P Wilson | 2023-05-21 | 2024-09-20 | 1987511 | 1545942 | 1233806 | 50 | Delayed | Low | 4.5 | 71
P260 | Audit Automation | UK | Tax | R Patel | 2025-09-23 | 2026-02-11 | 499436 | 401400 | 438203 | 36 | Delayed | Low | 3 | 48
P261 | Cyber Review | US | Consulting | K Gupta | 2024-09-15 | 2025-04-23 | 489089 | 371973 | 521219 | 6 | Completed | Medium | 2.6 | 100
P262 | Finance Transformation | Germany | Technology | M Brown | 2024-07-04 | 2025-02-26 | 1276456 | 1022045 | 1074024 | 50 | Completed | High | 2 | 100
P263 | AI Enablement | Germany | Risk Advisory | J Smith | 2025-02-12 | 2026-01-25 | 1859519 | 1836733 | 2092885 | 33 | Active | Medium | 4.1 | 87
P264 | Risk Assessment | Australia | Risk Advisory | K Gupta | 2023-05-13 | 2023-12-17 | 650092 | 499104 | 473477 | 46 | On Hold | Medium | 3.3 | 26
P265 | Cyber Review | Germany | Technology | S Lee | 2023-06-18 | 2023-09-15 | 614620 | 521504 | 386903 | 3 | Delayed | Medium | 1.2 | 73
P266 | Data Modernization | US | Risk Advisory | P Wilson | 2024-03-02 | 2025-06-05 | 722347 | 751124 | 670616 | 24 | Active | Low | 4.8 | 34
P267 | Data Modernization | Singapore | Risk Advisory | K Gupta | 2024-01-20 | 2025-07-05 | 1466930 | 1253367 | 1458255 | 41 | Completed | High | 4.3 | 100
P268 | Cyber Review | UK | Audit | P Wilson | 2024-02-22 | 2024-05-16 | 107505 | 103192 | 124092 | 41 | Active | High | 4.6 | 57
P269 | Cloud Strategy | India | Consulting | A Sharma | 2023-11-18 | 2024-09-16 | 1118474 | 847027 | 1194927 | 33 | Completed | Medium | 3 | 100
P270 | ERP Migration | India | Risk Advisory | S Lee | 2023-02-08 | 2023-11-11 | 623230 | 530801 | 569567 | 37 | Completed | Medium | 4.7 | 100
P271 | Cloud Strategy | Germany | Tax | K Gupta | 2024-04-17 | 2025-05-11 | 194919 | 153495 | 153425 | 26 | Delayed | High | 3.1 | 14
P272 | Audit Automation | UK | Tax | K Gupta | 2024-11-25 | 2026-04-14 | 1567307 | 1409107 | 2157446 | 3 | Completed | Medium | 4.9 | 100
P273 | Tax Transformation | Germany | Risk Advisory | K Gupta | 2023-08-20 | 2023-10-21 | 861308 | 770056 | 639126 | 48 | Delayed | Medium | 2.1 | 21
P274 | Cloud Strategy | US | Audit | M Brown | 2024-12-30 | 2026-05-20 | 1986937 | 1876772 | 2406253 | 5 | Completed | Medium | 1.4 | 100
P275 | Data Modernization | US | Consulting | T Johnson | 2025-05-24 | 2025-10-24 | 558450 | 562723 | 418293 | 29 | Delayed | Medium | 1.6 | 62
P276 | AI Enablement | Singapore | Risk Advisory | J Smith | 2024-01-12 | 2024-05-13 | 1876577 | 1906321 | 1538462 | 34 | Delayed | Medium | 3.1 | 44
P277 | PMO Support | UK | Consulting | N Singh | 2025-09-01 | 2025-12-06 | 110551 | 108595 | 99498 | 8 | On Hold | Medium | 2.9 | 38
P278 | Risk Assessment | Australia | Consulting | K Gupta | 2023-02-10 | 2023-07-29 | 1194928 | 1226596 | 906181 | 17 | Delayed | Low | 3.5 | 79
P279 | Risk Assessment | UK | Consulting | S Lee | 2024-10-02 | 2025-01-15 | 1792179 | 1414789 | 2197145 | 20 | Completed | Medium | 5 | 100
P280 | Tax Transformation | US | Tax | R Patel | 2025-01-24 | 2025-07-27 | 1201235 | 1375697 | 1915198 | 11 | Completed | High | 3.2 | 100
P281 | ERP Migration | Australia | Risk Advisory | K Gupta | 2024-03-02 | 2024-11-09 | 1908162 | 2086451 | 2446662 | 50 | Completed | Low | 3.7 | 100
P282 | PMO Support | Australia | Audit | S Lee | 2023-08-24 | 2025-02-02 | 540700 | 460338 | 368518 | 37 | On Hold | Medium | 1.7 | 7
P283 | Risk Assessment | Australia | Consulting | S Lee | 2024-12-15 | 2025-02-24 | 160573 | 153641 | 181509 | 29 | Active | Low | 3.7 | 57
P284 | ERP Migration | UK | Technology | T Johnson | 2024-06-17 | 2025-01-07 | 773415 | 776532 | 981468 | 9 | Completed | High | 3.7 | 100
P285 | Cyber Review | Germany | Risk Advisory | S Lee | 2024-11-12 | 2025-12-05 | 958305 | 831311 | 713588 | 10 | Delayed | Low | 2.2 | 56
P286 | AI Enablement | Singapore | Audit | S Lee | 2023-09-16 | 2024-09-20 | 1252785 | 1254441 | 1135393 | 3 | Active | Medium | 4 | 49
P287 | Data Modernization | US | Technology | T Johnson | 2025-06-08 | 2026-05-15 | 783425 | 612060 | 350832 | 16 | On Hold | Low | 4.6 | 34
P288 | Data Modernization | Australia | Risk Advisory | R Patel | 2024-11-26 | 2025-03-11 | 883783 | 677462 | 911906 | 21 | Completed | High | 2.3 | 100
P289 | Cyber Review | Singapore | Technology | A Sharma | 2024-11-30 | 2026-03-08 | 1633529 | 1714791 | 2229178 | 23 | Active | High | 2.4 | 82
P290 | ERP Migration | India | Technology | R Patel | 2024-03-17 | 2025-06-10 | 334961 | 305233 | 218723 | 37 | On Hold | Medium | 1.1 | 56
P291 | PMO Support | Australia | Tax | T Johnson | 2024-01-09 | 2024-09-24 | 258763 | 237362 | 222574 | 5 | Delayed | Medium | 4.6 | 64
P292 | Cyber Review | US | Tax | D Kumar | 2024-10-27 | 2026-02-06 | 1285441 | 1443756 | 1204449 | 32 | On Hold | Medium | 2.8 | 20
P293 | Tax Transformation | Germany | Consulting | R Patel | 2025-02-19 | 2026-05-31 | 1514644 | 1678973 | 1557720 | 22 | Active | High | 3.9 | 65
P294 | Finance Transformation | Singapore | Consulting | D Kumar | 2024-11-13 | 2025-11-03 | 860368 | 663618 | 422525 | 49 | On Hold | High | 1 | 34
P295 | Finance Transformation | Germany | Tax | M Brown | 2025-01-23 | 2025-08-16 | 1760271 | 1934310 | 2511938 | 25 | Active | High | 4.7 | 95
P296 | Risk Assessment | India | Technology | A Sharma | 2023-07-14 | 2023-12-13 | 113975 | 91893 | 100296 | 27 | Delayed | High | 3.6 | 55
P297 | Data Modernization | US | Risk Advisory | T Johnson | 2023-03-19 | 2023-06-17 | 1823862 | 1914747 | 2342812 | 49 | Completed | High | 4.5 | 100
P298 | Cloud Strategy | Germany | Audit | P Wilson | 2025-06-08 | 2026-04-26 | 174849 | 138682 | 205487 | 14 | Completed | Medium | 2.7 | 100
P299 | Cyber Review | UK | Consulting | S Lee | 2024-07-26 | 2024-12-17 | 564491 | 499723 | 605529 | 36 | Active | Low | 2.8 | 91
P300 | Finance Transformation | Germany | Tax | R Patel | 2023-05-06 | 2024-04-18 | 1219770 | 1281436 | 679717 | 31 | On Hold | Low | 1.6 | 38
P301 | AI Enablement | Germany | Tax | K Gupta | 2023-06-07 | 2023-09-10 | 575382 | 593789 | 410403 | 42 | On Hold | Low | 1.6 | 23
P302 | Tax Transformation | Germany | Risk Advisory | R Patel | 2025-01-04 | 2025-08-19 | 402883 | 363929 | 464570 | 20 | Completed | High | 3.5 | 100
P303 | Finance Transformation | Australia | Audit | T Johnson | 2023-06-07 | 2024-03-28 | 305105 | 279181 | 235589 | 11 | Delayed | Low | 3.8 | 51
P304 | Risk Assessment | India | Consulting | P Wilson | 2023-09-14 | 2025-03-04 | 1425667 | 1270286 | 1037519 | 19 | Active | Low | 1 | 46
P305 | Audit Automation | Germany | Tax | P Wilson | 2024-08-09 | 2025-12-23 | 230075 | 254677 | 262896 | 17 | On Hold | Low | 4.9 | 31
P306 | Risk Assessment | India | Tax | M Brown | 2023-04-19 | 2024-07-06 | 187682 | 180339 | 257899 | 32 | Completed | Medium | 4.6 | 100
P307 | Tax Transformation | India | Risk Advisory | A Sharma | 2024-02-15 | 2025-02-26 | 844515 | 824261 | 1316165 | 48 | Completed | Low | 4.6 | 100
P308 | Cloud Strategy | Singapore | Technology | M Brown | 2024-11-26 | 2026-04-05 | 1619374 | 1658234 | 1415956 | 7 | On Hold | High | 1.9 | 15
P309 | PMO Support | US | Audit | D Kumar | 2023-01-01 | 2023-12-28 | 1936306 | 1793625 | 2456062 | 37 | Completed | Low | 4.2 | 100
P310 | Cloud Strategy | Germany | Tax | J Smith | 2023-08-19 | 2024-08-18 | 1368173 | 1098192 | 1728526 | 20 | Completed | Medium | 4 | 100
P311 | Cloud Strategy | Australia | Tax | S Lee | 2024-11-06 | 2025-11-11 | 530958 | 537298 | 606717 | 29 | Completed | High | 2.3 | 100
P312 | Risk Assessment | UK | Tax | M Brown | 2023-11-16 | 2024-11-17 | 238272 | 255618 | 319316 | 24 | Completed | High | 4.5 | 100
P313 | Tax Transformation | Germany | Consulting | R Patel | 2025-04-29 | 2025-10-29 | 1155588 | 968009 | 1253725 | 5 | Completed | Medium | 3.6 | 100
P314 | Finance Transformation | US | Audit | A Sharma | 2025-09-03 | 2026-02-22 | 1510523 | 1150308 | 835263 | 3 | Delayed | Medium | 3.8 | 86
P315 | Data Modernization | Australia | Consulting | N Singh | 2023-11-25 | 2024-12-21 | 1625703 | 1446883 | 1358323 | 42 | Delayed | Medium | 1.9 | 34
P316 | Cloud Strategy | India | Tax | A Sharma | 2024-10-12 | 2025-07-31 | 666652 | 614352 | 614128 | 42 | Delayed | Medium | 2.5 | 63
P317 | Finance Transformation | US | Consulting | P Wilson | 2025-02-19 | 2026-08-06 | 458497 | 518318 | 599610 | 33 | Active | High | 3.7 | 74
P318 | ERP Migration | Singapore | Technology | M Brown | 2023-09-14 | 2024-09-23 | 213581 | 205868 | 273913 | 45 | Completed | Medium | 4.1 | 100
P319 | Tax Transformation | UK | Technology | R Patel | 2025-03-18 | 2025-07-27 | 583309 | 450565 | 556048 | 25 | Completed | High | 3.9 | 100
P320 | ERP Migration | Singapore | Consulting | A Sharma | 2023-02-08 | 2023-11-28 | 1770786 | 1969208 | 1276549 | 30 | On Hold | High | 3.9 | 11
P321 | Cyber Review | UK | Audit | T Johnson | 2025-04-24 | 2026-10-12 | 1606743 | 1601650 | 1364982 | 21 | Delayed | High | 1.9 | 11
P322 | ERP Migration | Germany | Consulting | S Lee | 2024-12-17 | 2026-05-16 | 429327 | 451567 | 490841 | 21 | On Hold | High | 1 | 50
P323 | PMO Support | UK | Risk Advisory | D Kumar | 2024-01-02 | 2024-04-12 | 273817 | 302185 | 193796 | 4 | On Hold | Medium | 4.7 | 59
P324 | Finance Transformation | India | Audit | N Singh | 2024-02-16 | 2024-05-02 | 1385278 | 1532528 | 1082922 | 17 | Delayed | High | 2.7 | 14
P325 | Risk Assessment | US | Risk Advisory | R Patel | 2025-05-07 | 2025-11-25 | 1935768 | 1608663 | 1236109 | 45 | Delayed | Low | 4.5 | 14
P326 | Finance Transformation | Australia | Risk Advisory | M Brown | 2024-09-19 | 2025-10-26 | 405890 | 372195 | 196441 | 3 | On Hold | Low | 3.9 | 56
P327 | Audit Automation | US | Consulting | M Brown | 2023-08-24 | 2024-12-27 | 676305 | 768766 | 757812 | 39 | On Hold | Medium | 4 | 52
P328 | ERP Migration | India | Tax | K Gupta | 2023-10-24 | 2024-02-22 | 485197 | 413378 | 478673 | 26 | Completed | Low | 3.5 | 100
P329 | Audit Automation | Singapore | Audit | P Wilson | 2023-07-08 | 2024-04-10 | 285336 | 310089 | 387345 | 33 | Completed | Low | 1.9 | 100
P330 | Cloud Strategy | India | Technology | R Patel | 2025-05-06 | 2026-01-09 | 1363927 | 1535612 | 775816 | 8 | On Hold | High | 2.1 | 7
P331 | Cyber Review | Singapore | Risk Advisory | S Lee | 2024-08-02 | 2024-11-16 | 1617765 | 1311205 | 1580904 | 35 | Completed | Low | 2.2 | 100
P332 | PMO Support | US | Technology | R Patel | 2023-01-05 | 2024-05-27 | 790902 | 781450 | 701454 | 33 | Active | Low | 2.2 | 37
P333 | PMO Support | US | Audit | P Wilson | 2024-08-01 | 2025-09-26 | 1446446 | 1373816 | 1050660 | 27 | Delayed | Low | 2.9 | 60
P334 | Risk Assessment | US | Audit | R Patel | 2024-03-25 | 2025-03-21 | 871681 | 713247 | 814501 | 20 | Active | High | 1.2 | 53
P335 | Risk Assessment | Australia | Tax | T Johnson | 2024-01-01 | 2024-09-17 | 1140326 | 1228653 | 1280621 | 45 | Delayed | Medium | 1.1 | 20
P336 | Finance Transformation | UK | Risk Advisory | D Kumar | 2024-12-25 | 2025-04-18 | 1103600 | 942739 | 1295379 | 47 | Completed | Low | 3.9 | 100
P337 | Cloud Strategy | Germany | Consulting | K Gupta | 2024-10-24 | 2025-03-07 | 251897 | 208403 | 145221 | 24 | On Hold | High | 4.5 | 36
P338 | Risk Assessment | US | Risk Advisory | K Gupta | 2024-05-04 | 2024-07-04 | 1327209 | 1314701 | 1077060 | 12 | Delayed | Medium | 1.8 | 56
P339 | ERP Migration | India | Consulting | K Gupta | 2023-06-18 | 2024-06-28 | 571382 | 573948 | 561023 | 50 | Delayed | High | 3.1 | 42
P340 | Audit Automation | Germany | Tax | M Brown | 2024-04-20 | 2025-01-16 | 1571666 | 1597260 | 1779901 | 26 | Active | Low | 2 | 74
P341 | Data Modernization | Singapore | Consulting | T Johnson | 2025-03-08 | 2026-07-11 | 270133 | 277894 | 231910 | 34 | Active | Low | 3.4 | 55
P342 | Cloud Strategy | Singapore | Consulting | T Johnson | 2023-12-04 | 2024-02-16 | 762351 | 698821 | 890754 | 22 | Active | Low | 1.3 | 23
P343 | ERP Migration | Singapore | Audit | M Brown | 2023-09-18 | 2024-04-01 | 1671574 | 1468848 | 1757877 | 43 | Active | Low | 3.1 | 67
P344 | Finance Transformation | India | Risk Advisory | P Wilson | 2024-09-04 | 2025-10-18 | 1168338 | 962972 | 1381284 | 6 | Completed | High | 1.2 | 100
P345 | Cyber Review | US | Risk Advisory | R Patel | 2025-03-08 | 2026-01-06 | 1246112 | 1240500 | 1761482 | 33 | Completed | High | 2.9 | 100
P346 | Cyber Review | Australia | Risk Advisory | M Brown | 2024-01-29 | 2024-10-19 | 707472 | 648398 | 624936 | 43 | Active | Low | 3.4 | 25
P347 | AI Enablement | Australia | Audit | S Lee | 2024-01-18 | 2025-03-07 | 1809134 | 1845568 | 1785654 | 7 | Active | Medium | 1.8 | 75
P348 | Audit Automation | Singapore | Audit | M Brown | 2023-09-09 | 2023-12-30 | 554334 | 491479 | 502401 | 6 | Active | Medium | 2.2 | 73
P349 | Cloud Strategy | US | Tax | P Wilson | 2023-07-04 | 2024-06-12 | 245591 | 191192 | 96280 | 49 | On Hold | High | 3.6 | 41
P350 | Audit Automation | US | Risk Advisory | J Smith | 2025-08-15 | 2026-12-25 | 1877038 | 1903327 | 1455558 | 21 | On Hold | High | 1.4 | 23
P351 | Tax Transformation | India | Technology | J Smith | 2025-02-01 | 2025-04-10 | 882227 | 679284 | 817688 | 22 | Active | Low | 3.7 | 52
P352 | Tax Transformation | US | Technology | R Patel | 2023-08-29 | 2024-07-02 | 153865 | 149120 | 215278 | 16 | Completed | Low | 4.6 | 100
P353 | Risk Assessment | Singapore | Technology | N Singh | 2024-09-12 | 2025-12-27 | 1003729 | 773901 | 994905 | 36 | Completed | Low | 2.9 | 100
P354 | Data Modernization | India | Audit | N Singh | 2024-01-19 | 2024-06-15 | 1630874 | 1438003 | 1275852 | 25 | Delayed | Low | 1.2 | 50
P355 | Cyber Review | US | Risk Advisory | D Kumar | 2024-09-21 | 2025-06-22 | 1235382 | 1229459 | 1268918 | 7 | On Hold | High | 2.3 | 41
P356 | Cyber Review | Singapore | Technology | D Kumar | 2024-06-28 | 2025-10-17 | 999633 | 1127708 | 1474947 | 45 | Completed | High | 4.5 | 100
P357 | Audit Automation | Australia | Audit | T Johnson | 2024-06-27 | 2025-08-25 | 1602255 | 1568733 | 1561202 | 35 | Active | Low | 2.6 | 88
P358 | Risk Assessment | India | Audit | P Wilson | 2023-06-17 | 2024-09-24 | 275673 | 279967 | 300028 | 30 | Active | Low | 2.4 | 52
P359 | Cyber Review | Germany | Consulting | T Johnson | 2024-06-20 | 2024-11-20 | 1814326 | 1610052 | 2013519 | 13 | Completed | Medium | 1 | 100
P360 | Cloud Strategy | India | Tax | K Gupta | 2023-11-02 | 2024-07-12 | 365423 | 329737 | 299608 | 44 | Delayed | Medium | 4.9 | 80
P361 | Cyber Review | Singapore | Technology | K Gupta | 2023-08-17 | 2024-11-27 | 1336391 | 1091855 | 1253757 | 21 | Completed | Low | 1.1 | 100
P362 | Data Modernization | India | Consulting | T Johnson | 2025-03-17 | 2026-07-22 | 875511 | 942410 | 840341 | 22 | Delayed | Medium | 1.6 | 49
P363 | Cyber Review | US | Audit | S Lee | 2023-10-07 | 2025-02-07 | 104758 | 99260 | 90784 | 23 | Active | Low | 4.1 | 38
P364 | Risk Assessment | India | Technology | D Kumar | 2024-02-18 | 2025-07-22 | 775665 | 834657 | 1029427 | 41 | Completed | Low | 2.8 | 100
P365 | PMO Support | Germany | Risk Advisory | R Patel | 2025-02-18 | 2025-10-31 | 1524734 | 1169563 | 1309803 | 13 | Delayed | Medium | 1.6 | 67
P366 | ERP Migration | Australia | Risk Advisory | S Lee | 2023-09-07 | 2024-11-17 | 1802114 | 1521264 | 906959 | 19 | On Hold | Low | 2.7 | 7
P367 | Audit Automation | US | Audit | T Johnson | 2023-10-27 | 2024-12-12 | 850149 | 878464 | 638860 | 26 | Delayed | Low | 3.5 | 33
P368 | Cloud Strategy | Singapore | Consulting | N Singh | 2024-10-13 | 2025-10-30 | 1730093 | 1431413 | 1716931 | 29 | Active | Medium | 3.2 | 73
P369 | ERP Migration | US | Audit | M Brown | 2024-08-18 | 2025-11-22 | 561089 | 635612 | 755146 | 22 | Completed | Medium | 3.2 | 100
P370 | Tax Transformation | Germany | Technology | S Lee | 2024-08-27 | 2025-12-02 | 573563 | 579529 | 574217 | 20 | On Hold | Low | 1.5 | 2
P371 | Finance Transformation | Singapore | Consulting | K Gupta | 2024-11-13 | 2025-08-28 | 852345 | 753935 | 691765 | 4 | On Hold | Low | 2.5 | 52
P372 | AI Enablement | US | Audit | A Sharma | 2023-04-28 | 2024-02-10 | 364568 | 282899 | 326395 | 10 | Delayed | Medium | 4 | 48
P373 | ERP Migration | Australia | Technology | J Smith | 2023-07-29 | 2024-03-09 | 1210418 | 1049552 | 1212800 | 31 | Delayed | High | 1.1 | 74
P374 | Audit Automation | Singapore | Audit | M Brown | 2025-09-06 | 2026-01-25 | 1014934 | 972047 | 498458 | 11 | On Hold | High | 4.4 | 13
P375 | Audit Automation | US | Risk Advisory | R Patel | 2023-02-22 | 2024-07-17 | 1095133 | 826102 | 1156989 | 30 | Completed | Low | 4.4 | 100
P376 | ERP Migration | Australia | Audit | P Wilson | 2023-03-05 | 2024-07-26 | 688276 | 775344 | 689145 | 34 | Delayed | Medium | 1.3 | 14
P377 | Risk Assessment | UK | Tax | P Wilson | 2025-02-04 | 2026-02-23 | 236637 | 226147 | 246633 | 6 | Delayed | Medium | 1.3 | 78
P378 | Risk Assessment | India | Risk Advisory | P Wilson | 2025-05-07 | 2026-05-11 | 994873 | 1092095 | 1093336 | 24 | On Hold | Low | 1.7 | 11
P379 | AI Enablement | Singapore | Consulting | M Brown | 2024-07-31 | 2025-10-25 | 744364 | 755459 | 823633 | 8 | Delayed | High | 2.3 | 78
P380 | Data Modernization | Singapore | Consulting | T Johnson | 2024-03-24 | 2025-08-25 | 327570 | 268927 | 216830 | 16 | Active | Medium | 3.6 | 72
P381 | Tax Transformation | Singapore | Tax | K Gupta | 2023-09-17 | 2024-10-06 | 1909655 | 1967781 | 993682 | 10 | On Hold | Low | 4.9 | 11
P382 | Cloud Strategy | US | Risk Advisory | A Sharma | 2024-07-25 | 2025-06-21 | 1533223 | 1302202 | 1657062 | 44 | Completed | Low | 4.5 | 100
P383 | AI Enablement | Australia | Risk Advisory | N Singh | 2024-03-31 | 2025-06-19 | 1981259 | 1529824 | 1586001 | 8 | Active | High | 1.6 | 26
P384 | Tax Transformation | Singapore | Consulting | J Smith | 2024-06-18 | 2025-01-05 | 197359 | 195142 | 247502 | 46 | Completed | Low | 4.6 | 100
P385 | Tax Transformation | UK | Audit | D Kumar | 2025-01-08 | 2025-11-16 | 1988041 | 1576777 | 1884619 | 43 | Delayed | Medium | 4.2 | 50
P386 | ERP Migration | Singapore | Audit | M Brown | 2025-07-28 | 2026-10-10 | 1638136 | 1240447 | 1157623 | 33 | Delayed | High | 4.1 | 69
P387 | PMO Support | US | Risk Advisory | R Patel | 2025-09-22 | 2026-11-18 | 988381 | 909269 | 748217 | 24 | Active | Medium | 4.2 | 26
P388 | Cloud Strategy | Germany | Tax | S Lee | 2024-01-13 | 2025-03-18 | 293848 | 272787 | 285296 | 44 | Delayed | Medium | 4 | 57
P389 | Risk Assessment | US | Technology | P Wilson | 2023-04-06 | 2024-01-12 | 473431 | 536724 | 521826 | 47 | On Hold | Low | 3.3 | 53
P390 | Cloud Strategy | US | Risk Advisory | D Kumar | 2024-04-27 | 2024-10-06 | 492449 | 508687 | 509460 | 21 | Active | Low | 1.3 | 73
P391 | Data Modernization | Singapore | Consulting | D Kumar | 2023-03-25 | 2024-08-23 | 1676725 | 1610639 | 1282080 | 8 | Delayed | Medium | 1.7 | 57
P392 | Finance Transformation | US | Technology | P Wilson | 2023-04-18 | 2023-07-18 | 1050758 | 980483 | 1048029 | 4 | Active | Low | 1.1 | 22
P393 | PMO Support | Australia | Technology | J Smith | 2025-03-28 | 2025-09-02 | 798900 | 681495 | 684988 | 23 | On Hold | Low | 2.1 | 24
P394 | Finance Transformation | US | Technology | K Gupta | 2024-12-17 | 2025-06-19 | 1488998 | 1377890 | 1106450 | 13 | Active | Medium | 4.1 | 89
P395 | Cloud Strategy | Singapore | Tax | M Brown | 2025-02-23 | 2025-06-13 | 1608565 | 1626926 | 1949363 | 44 | Active | Low | 4.3 | 42
P396 | PMO Support | US | Tax | S Lee | 2025-03-25 | 2026-06-14 | 1087350 | 998520 | 1401130 | 11 | Completed | Medium | 2.5 | 100
P397 | Finance Transformation | US | Audit | M Brown | 2024-12-01 | 2025-09-10 | 353174 | 303219 | 369862 | 23 | Completed | High | 3.2 | 100
P398 | PMO Support | India | Technology | N Singh | 2023-04-24 | 2023-08-01 | 953234 | 1027559 | 976582 | 39 | Delayed | Low | 4.2 | 48
P399 | Risk Assessment | Germany | Technology | T Johnson | 2025-02-13 | 2025-12-17 | 365855 | 394298 | 206130 | 45 | On Hold | Medium | 1.4 | 38
P400 | ERP Migration | Australia | Risk Advisory | K Gupta | 2023-12-23 | 2024-09-06 | 1110506 | 1123768 | 1113261 | 8 | Active | Medium | 3.4 | 77
P401 | Finance Transformation | UK | Technology | T Johnson | 2025-06-15 | 2025-08-30 | 1397562 | 1571621 | 2439642 | 5 | Completed | High | 3 | 100
P402 | Finance Transformation | Australia | Risk Advisory | T Johnson | 2023-10-17 | 2025-01-07 | 212115 | 183236 | 155011 | 42 | On Hold | High | 2.2 | 30
P403 | Tax Transformation | US | Technology | P Wilson | 2025-09-05 | 2026-03-10 | 931107 | 1028078 | 802280 | 15 | Delayed | Low | 1.3 | 74
P404 | Cyber Review | India | Technology | A Sharma | 2025-06-27 | 2026-06-24 | 1845297 | 1412595 | 2130341 | 3 | Completed | Low | 4.9 | 100
P405 | ERP Migration | Australia | Technology | N Singh | 2024-07-23 | 2025-05-03 | 294936 | 231532 | 239945 | 31 | On Hold | Low | 3.6 | 49
P406 | Tax Transformation | India | Tax | R Patel | 2025-04-06 | 2026-01-17 | 1500327 | 1567395 | 1987299 | 14 | Completed | High | 1.3 | 100
P407 | Finance Transformation | Australia | Tax | T Johnson | 2023-09-23 | 2023-12-11 | 261356 | 228686 | 301707 | 3 | Completed | High | 3.1 | 100
P408 | AI Enablement | India | Consulting | T Johnson | 2025-05-08 | 2026-07-15 | 678938 | 591501 | 428183 | 37 | On Hold | High | 2.3 | 51
P409 | Audit Automation | Germany | Tax | J Smith | 2025-07-26 | 2026-11-11 | 114502 | 94658 | 89822 | 41 | Active | High | 2.5 | 57
P410 | PMO Support | US | Audit | T Johnson | 2025-01-31 | 2025-04-24 | 1953047 | 2056923 | 1032392 | 43 | On Hold | Low | 3.1 | 5
P411 | Cloud Strategy | Germany | Technology | S Lee | 2023-04-04 | 2024-06-20 | 601178 | 527713 | 642315 | 49 | Active | High | 3 | 54
P412 | PMO Support | Singapore | Risk Advisory | R Patel | 2023-12-18 | 2025-03-09 | 1610487 | 1405671 | 1032682 | 14 | Delayed | Medium | 1.5 | 24
P413 | Cyber Review | India | Technology | P Wilson | 2024-01-22 | 2024-05-18 | 796955 | 661182 | 685464 | 26 | Delayed | Medium | 2.7 | 79
P414 | Finance Transformation | Singapore | Consulting | K Gupta | 2025-05-18 | 2026-03-27 | 1104754 | 1221841 | 862744 | 48 | Delayed | High | 1.7 | 52
P415 | Cyber Review | Germany | Consulting | K Gupta | 2024-05-28 | 2025-08-29 | 1945342 | 1918311 | 1643346 | 49 | Active | Low | 3.9 | 20
P416 | Finance Transformation | UK | Technology | D Kumar | 2024-01-12 | 2025-02-26 | 1847251 | 1527391 | 1957558 | 33 | Completed | Low | 3.6 | 100
P417 | Data Modernization | Singapore | Consulting | K Gupta | 2025-07-07 | 2026-10-11 | 1554108 | 1174427 | 1521525 | 22 | Completed | Low | 1.4 | 100
P418 | AI Enablement | US | Tax | A Sharma | 2023-07-11 | 2024-10-01 | 222337 | 174278 | 209455 | 25 | Completed | High | 1 | 100
P419 | Data Modernization | Germany | Consulting | A Sharma | 2025-02-11 | 2025-04-21 | 833247 | 928567 | 1044316 | 12 | Delayed | Medium | 2.1 | 60
P420 | Cloud Strategy | India | Audit | R Patel | 2024-07-15 | 2025-12-23 | 1072481 | 1165193 | 696682 | 38 | On Hold | Low | 3.9 | 15
P421 | Cyber Review | Australia | Consulting | M Brown | 2023-12-27 | 2025-05-26 | 1451256 | 1088524 | 1164743 | 46 | Completed | Low | 3.8 | 100
P422 | Tax Transformation | Singapore | Technology | M Brown | 2023-09-11 | 2024-06-09 | 1233026 | 1141863 | 1249691 | 34 | Active | High | 2.5 | 23
P423 | Audit Automation | India | Risk Advisory | J Smith | 2024-08-17 | 2026-01-10 | 1491039 | 1495336 | 1316228 | 42 | Delayed | Low | 3.3 | 50
P424 | AI Enablement | US | Technology | K Gupta | 2025-02-06 | 2025-10-30 | 854617 | 924443 | 1068764 | 9 | Active | High | 4 | 59
P425 | Tax Transformation | Germany | Technology | P Wilson | 2025-01-14 | 2026-02-06 | 682489 | 720403 | 665282 | 39 | Active | Low | 1.7 | 53
P426 | ERP Migration | Singapore | Risk Advisory | J Smith | 2023-05-29 | 2023-12-30 | 203515 | 160220 | 243031 | 27 | Completed | Low | 5 | 100
P427 | Cloud Strategy | Germany | Audit | S Lee | 2023-03-20 | 2023-05-21 | 500989 | 489586 | 564195 | 32 | Delayed | High | 2 | 63
P428 | Risk Assessment | Germany | Audit | M Brown | 2025-01-01 | 2025-09-24 | 1998970 | 1692895 | 2109019 | 24 | Active | Medium | 2.3 | 82
P429 | Risk Assessment | US | Audit | A Sharma | 2025-01-02 | 2025-12-09 | 1730892 | 1510782 | 1536149 | 7 | On Hold | Medium | 1.8 | 24
P430 | ERP Migration | Australia | Technology | P Wilson | 2025-06-30 | 2026-09-30 | 329350 | 297520 | 191464 | 25 | On Hold | High | 3.9 | 47
P431 | Risk Assessment | Singapore | Audit | M Brown | 2024-10-11 | 2025-04-02 | 1073196 | 974801 | 1135241 | 28 | Delayed | High | 3.2 | 33
P432 | Finance Transformation | Germany | Consulting | N Singh | 2025-03-23 | 2026-04-02 | 1363962 | 1322886 | 1369310 | 50 | Delayed | High | 4.7 | 75
P433 | Risk Assessment | Singapore | Risk Advisory | A Sharma | 2025-08-02 | 2026-11-03 | 850881 | 858547 | 934004 | 43 | On Hold | Medium | 3.1 | 12
P434 | Data Modernization | Singapore | Risk Advisory | R Patel | 2025-09-26 | 2027-01-12 | 1521476 | 1645394 | 1980646 | 43 | Active | Low | 3.8 | 23
P435 | Tax Transformation | Germany | Tax | S Lee | 2024-05-25 | 2025-03-06 | 1320888 | 1151028 | 1623972 | 13 | Completed | Medium | 1.1 | 100
P436 | Data Modernization | Australia | Audit | M Brown | 2023-08-30 | 2023-11-03 | 556063 | 432276 | 666536 | 25 | Completed | Medium | 4.3 | 100
P437 | ERP Migration | Germany | Technology | P Wilson | 2023-10-08 | 2024-09-23 | 925178 | 882623 | 1091211 | 30 | Completed | Low | 4.1 | 100
P438 | Cloud Strategy | Singapore | Tax | J Smith | 2023-07-23 | 2024-07-17 | 841550 | 668105 | 798712 | 18 | Active | High | 1.4 | 23
P439 | Tax Transformation | UK | Risk Advisory | N Singh | 2023-12-28 | 2025-05-16 | 1776842 | 2001517 | 1034035 | 35 | On Hold | Low | 1.6 | 59
P440 | Finance Transformation | Singapore | Risk Advisory | J Smith | 2023-03-10 | 2023-08-30 | 329059 | 330695 | 273233 | 23 | On Hold | Medium | 4.1 | 8
P441 | Tax Transformation | UK | Tax | P Wilson | 2024-12-27 | 2025-03-30 | 1845377 | 1422662 | 1679640 | 33 | Completed | Medium | 3.6 | 100
P442 | Cloud Strategy | UK | Tax | K Gupta | 2023-12-25 | 2024-06-15 | 1857698 | 1639571 | 2616767 | 17 | Completed | Medium | 4.8 | 100
P443 | Audit Automation | Australia | Risk Advisory | R Patel | 2023-07-09 | 2024-04-23 | 1811841 | 1394719 | 2173383 | 50 | Completed | High | 2.9 | 100
P444 | Cyber Review | India | Consulting | S Lee | 2024-04-05 | 2025-01-24 | 1987679 | 2016658 | 2181946 | 25 | Delayed | High | 2.5 | 90
P445 | Audit Automation | US | Technology | R Patel | 2023-02-18 | 2024-03-27 | 1470950 | 1529615 | 2026821 | 12 | Completed | Medium | 3 | 100
P446 | Tax Transformation | Australia | Audit | S Lee | 2023-01-12 | 2023-03-21 | 570210 | 568820 | 675712 | 27 | Completed | High | 4.6 | 100
P447 | Finance Transformation | Singapore | Risk Advisory | A Sharma | 2025-01-16 | 2025-05-13 | 1106221 | 872393 | 969550 | 30 | Active | High | 3.9 | 27
P448 | Data Modernization | India | Tax | P Wilson | 2023-06-12 | 2024-03-03 | 1314871 | 1473852 | 1034493 | 40 | Delayed | Low | 2.8 | 66
P449 | Finance Transformation | Germany | Audit | N Singh | 2024-05-17 | 2025-06-30 | 1931623 | 2217075 | 1537372 | 22 | On Hold | Medium | 2.7 | 29
P450 | Tax Transformation | Australia | Consulting | T Johnson | 2024-07-05 | 2024-10-13 | 824843 | 698860 | 770554 | 28 | Active | Medium | 4.5 | 75
P451 | AI Enablement | Germany | Tax | M Brown | 2024-09-03 | 2025-09-07 | 1242029 | 1006536 | 1136785 | 39 | Completed | Medium | 1.4 | 100
P452 | Cyber Review | US | Risk Advisory | R Patel | 2024-07-27 | 2025-06-18 | 1262522 | 985077 | 1030310 | 15 | Active | Low | 4.4 | 31
P453 | Audit Automation | India | Risk Advisory | S Lee | 2024-06-12 | 2025-03-02 | 411808 | 383420 | 490836 | 23 | Active | High | 2.7 | 33
P454 | Cloud Strategy | UK | Audit | M Brown | 2024-09-05 | 2024-11-07 | 1391246 | 1566762 | 2386221 | 23 | Completed | High | 4.4 | 100
P455 | Audit Automation | Singapore | Audit | S Lee | 2023-02-22 | 2023-12-20 | 779561 | 624178 | 522034 | 45 | Delayed | Medium | 4.2 | 60
P456 | PMO Support | UK | Technology | K Gupta | 2025-04-28 | 2025-09-04 | 675761 | 622445 | 588893 | 18 | Delayed | Low | 1.8 | 73
P457 | Audit Automation | US | Tax | D Kumar | 2023-02-23 | 2023-11-19 | 1204958 | 1318133 | 864839 | 6 | On Hold | Medium | 3.1 | 36
P458 | ERP Migration | Singapore | Risk Advisory | M Brown | 2025-05-07 | 2026-03-12 | 896019 | 853532 | 1223155 | 10 | Completed | Medium | 2.6 | 100
P459 | Tax Transformation | UK | Audit | A Sharma | 2023-01-04 | 2024-02-03 | 1321281 | 1130699 | 844567 | 49 | Delayed | Medium | 1.3 | 39
P460 | Risk Assessment | India | Audit | J Smith | 2024-10-24 | 2025-06-02 | 907264 | 755678 | 858964 | 23 | Completed | Low | 5 | 100
P461 | Audit Automation | UK | Consulting | R Patel | 2023-05-26 | 2023-09-17 | 1320524 | 1184808 | 1605062 | 36 | Completed | Low | 2.6 | 100
P462 | Risk Assessment | UK | Technology | S Lee | 2023-05-29 | 2024-03-23 | 1934199 | 1482454 | 1504005 | 34 | Delayed | Low | 3.2 | 29
P463 | Audit Automation | Singapore | Tax | A Sharma | 2024-02-14 | 2025-05-22 | 1211586 | 1256254 | 1327638 | 26 | Completed | High | 2.2 | 100
P464 | Cloud Strategy | Australia | Audit | A Sharma | 2025-03-10 | 2025-11-02 | 1198861 | 999517 | 1165979 | 15 | Active | Medium | 1.9 | 79
P465 | Data Modernization | Australia | Risk Advisory | R Patel | 2024-06-10 | 2024-09-29 | 624165 | 544187 | 447123 | 4 | On Hold | Low | 2.4 | 0
P466 | Cloud Strategy | Singapore | Risk Advisory | P Wilson | 2024-05-18 | 2025-08-26 | 898835 | 976494 | 609295 | 26 | On Hold | Low | 1.6 | 52
P467 | Tax Transformation | UK | Tax | J Smith | 2025-04-15 | 2025-10-25 | 1246540 | 1166510 | 1327917 | 28 | Completed | High | 5 | 100
P468 | Cyber Review | US | Tax | S Lee | 2024-12-11 | 2025-06-26 | 1174957 | 1004940 | 1288661 | 6 | Active | High | 1 | 83
P469 | PMO Support | US | Consulting | A Sharma | 2025-09-16 | 2027-03-02 | 885860 | 670620 | 575676 | 46 | Active | Low | 2.4 | 82
P470 | Data Modernization | US | Tax | T Johnson | 2025-05-05 | 2025-09-15 | 507680 | 531719 | 500353 | 28 | On Hold | High | 4.4 | 16
P471 | Finance Transformation | India | Audit | A Sharma | 2023-12-08 | 2025-05-25 | 1682761 | 1780924 | 1389695 | 40 | Delayed | Low | 3.1 | 81
P472 | Audit Automation | Singapore | Risk Advisory | J Smith | 2025-07-03 | 2026-08-31 | 1280235 | 1392997 | 1212668 | 32 | On Hold | Medium | 3.1 | 60
P473 | AI Enablement | Singapore | Technology | P Wilson | 2023-03-27 | 2024-08-28 | 839243 | 903043 | 515676 | 47 | On Hold | Medium | 1.4 | 24
P474 | Finance Transformation | UK | Technology | N Singh | 2024-05-14 | 2024-12-23 | 874161 | 953378 | 917410 | 30 | Delayed | High | 3.6 | 15
P475 | Tax Transformation | India | Tax | R Patel | 2025-03-14 | 2026-02-05 | 731266 | 742764 | 938504 | 32 | Active | Low | 3.3 | 29
P476 | Cyber Review | UK | Risk Advisory | K Gupta | 2023-06-04 | 2023-10-13 | 1675218 | 1664495 | 1644393 | 43 | Delayed | Low | 2.8 | 55
P477 | PMO Support | India | Risk Advisory | A Sharma | 2025-08-09 | 2026-03-14 | 1159614 | 1259096 | 1477447 | 9 | Active | Medium | 4.5 | 36
P478 | Audit Automation | Australia | Risk Advisory | D Kumar | 2025-06-16 | 2025-12-05 | 1396073 | 1148992 | 1384168 | 48 | Active | Medium | 3.8 | 92
P479 | Finance Transformation | Australia | Technology | R Patel | 2023-07-05 | 2024-03-05 | 1852279 | 1924208 | 1664799 | 26 | Delayed | Medium | 4.8 | 36
P480 | Audit Automation | India | Risk Advisory | P Wilson | 2023-06-30 | 2023-11-03 | 842337 | 736942 | 621328 | 31 | On Hold | Medium | 3.9 | 30
P481 | Finance Transformation | Australia | Tax | A Sharma | 2023-04-14 | 2023-08-26 | 1362484 | 1470419 | 1439752 | 47 | Active | Medium | 1 | 51
P482 | Audit Automation | Germany | Consulting | N Singh | 2024-11-06 | 2026-02-17 | 298891 | 261247 | 273139 | 16 | On Hold | Medium | 2.2 | 44
P483 | Finance Transformation | US | Consulting | K Gupta | 2025-07-31 | 2025-10-28 | 445496 | 391060 | 394352 | 44 | Delayed | High | 1.5 | 84
P484 | Risk Assessment | Singapore | Risk Advisory | P Wilson | 2024-01-08 | 2024-10-07 | 108671 | 105094 | 73133 | 18 | On Hold | High | 4 | 8
P485 | Audit Automation | Australia | Audit | J Smith | 2025-08-20 | 2026-06-07 | 1947465 | 1771094 | 2650034 | 9 | Completed | High | 3.5 | 100
P486 | Tax Transformation | Singapore | Technology | D Kumar | 2023-12-10 | 2025-02-21 | 1942883 | 2098813 | 2483843 | 30 | Completed | High | 2.5 | 100
P487 | PMO Support | Australia | Tax | T Johnson | 2025-08-03 | 2026-06-26 | 822261 | 734321 | 527341 | 44 | On Hold | Low | 3.2 | 14
P488 | Audit Automation | UK | Consulting | S Lee | 2024-01-25 | 2025-01-08 | 1881307 | 1692068 | 1032474 | 22 | On Hold | High | 2.4 | 38
P489 | Finance Transformation | Australia | Tax | R Patel | 2025-06-01 | 2026-01-20 | 1045850 | 1079953 | 1132546 | 17 | Active | Low | 2.3 | 45
P490 | PMO Support | UK | Audit | K Gupta | 2024-01-12 | 2025-04-12 | 1017027 | 886321 | 914184 | 30 | On Hold | Low | 3.3 | 45
P491 | Tax Transformation | US | Consulting | A Sharma | 2025-04-16 | 2026-06-30 | 827182 | 850170 | 823369 | 20 | Delayed | Medium | 1.8 | 56
P492 | ERP Migration | Germany | Consulting | S Lee | 2023-04-26 | 2024-06-28 | 1137286 | 1092303 | 816318 | 36 | Delayed | Low | 4.4 | 51
P493 | ERP Migration | Germany | Tax | T Johnson | 2025-05-29 | 2026-08-30 | 1863295 | 1692623 | 2528007 | 38 | Completed | High | 4.5 | 100
P494 | ERP Migration | UK | Audit | M Brown | 2023-01-02 | 2023-04-10 | 640807 | 627453 | 920321 | 28 | Completed | High | 3.3 | 100
P495 | ERP Migration | Germany | Risk Advisory | R Patel | 2024-05-18 | 2025-02-06 | 317911 | 358802 | 436812 | 27 | Completed | Low | 3.9 | 100
P496 | Cyber Review | Germany | Consulting | A Sharma | 2024-05-09 | 2025-10-28 | 1260436 | 1217478 | 1317963 | 31 | Active | Low | 3.1 | 41
P497 | Cloud Strategy | UK | Tax | M Brown | 2025-02-26 | 2026-05-01 | 1185528 | 1309917 | 750469 | 26 | On Hold | Low | 4.2 | 23
P498 | PMO Support | Australia | Tax | R Patel | 2023-02-13 | 2023-11-29 | 345781 | 336807 | 256331 | 20 | Delayed | Medium | 4.4 | 44
P499 | Cloud Strategy | India | Technology | D Kumar | 2023-08-29 | 2024-01-01 | 495471 | 493174 | 505317 | 40 | Active | High | 1.8 | 94
P500 | Cloud Strategy | Australia | Tax | R Patel | 2025-03-05 | 2026-06-05 | 1796614 | 2009739 | 1781920 | 32 | Delayed | Low | 3.4 | 76